## Slide 1: UTSA Student Branch Projects Report Spring 2014
IEEE Central Texas Section
January 25th, 2014
San Marcos, Texas

## Slide 2
Phase I Projects |  |  |  |  | 
Short Name | Amount $ Budgeted | Amount $ Expended | Percent $ Expended | Percent Effort Complete | Plan to Complete
Promotion Membership Events IEEE Seminars | $300 | $290 | 96% | 100% | Fall 2013
Student Interest Groups Robotics | $200 | $100 | 50% | 50% | Mid-Spring 2014
Membership Incentives | $100 | $0 | 0% | 25% Design | Mid-Spring 2014

## Slide 3
Phase II Projects |  |  |  |  | 
Short Name | Amount $ Budgeted | Amount $ Expended | Percent $ Expended | Percent Effort Complete | Plan to Complete
Promotion | $100 | $5 | 5% | 5% | Early - Late Spring 2014
Membership Events | $300 | $0 | 0% | 0% | Early – Late Spring 2014
Student Interest Groups Robotics | $600 | $150 | 25% | 25% | Mid-Spring 2014
IEEE Seminars | $400 | $100 | 25% | 25% | Late-Spring 2014
S-PAC | $300 | $0 | 0% | 0% | Fall 2014 Planning
Membership Incentives | $300 | $0 | 0% | 0% | Mid-Spring 2014

## Slide 4: Questions?