## Sheet2
S/N | ACTIVITIES | EXPECTED RESULTS | IMPLEMENTING OFFICER(NAME) | COORDINATING COMMITTEE | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | FINANCIAL NEEDS (UGX)
Objective 1: Formation of an IEEE Kyambogo University student Branch
A.1 | Helping students with registration,forming a constitution and signing the petition for formation of the student branch | Formation of the IEEE kyu-student Branch | IEEE volunteers, Derrick, Allan | [13 empty] | 0 | bar: FEB to MAR
Objective 2: To create awareness about IEEE and increase student membership and participation
B.1 | IEEE seminar held at CTF | Increased awareness | Electrical Dept | bar: FEB
B.2 | Membership drives( targeting freshers) | Increase student membership | All members | Membership Committee, Executive committee | [12 empty] | 30000 | bar: AUG
B.3 | Publication of a monthly Branch news letter | Increased awareness | Branch secretary, All members | Publicity committee, Executive commiitee | [12 empty] | 0 | bar: MAR to DEC
Objective 3: Professional Development in Telecommunications, Electrical and Computing Technologies and Industry
C.1 | Student Professional Awareness Conference (SPAC) | Student professional Development | IEEE volunteers | Executive committee, all members | bar: AUG
C.2 | Schedule Speakers on professional and technical subjects (Monthly Public Lectures) | student professional development and exposure |  | Executive committee | [12 empty] | 20000 | bar: APR to DEC
C.3 | Participation in IEEE conferences | Exposure and networking | all members | bar: MAR to DEC
Objective 4 : Projects
D.1 | Establishment of a student Branch Website | Skills Development | Web master (Dan Ahimbisibwe) | Executive committee, all members | bar: MAR
D.2 | Creation of a SIGHT Group, proposal writing and building various projects) | Skills and Project development | IEEE volunteers together with the Branch conselor | [13 empty] | Discusion as Project will need | bar: MAR to DEC
Objective 5: Handover and Closure
E.1 | Submission of annual Activity report | To get funding from IEEE for the new year | Chair , Secretary, Treasurer | Executive Committee | bar: OCT to NOV
E.2 | Elections of New leadership | Continuity of IEEE Kyu student Branch |  | Normination Committee | bar: NOV
E.3 | IEEE Annual Dinner | Networking and Handover | IEEE Uganda Subsection Committee | bar: DEC
Compiled by: Byarugaba Derrick Branch Chair