The Meeting Minutes on 26 Aug’05 (ICIEA 2006)

(Draft for discussion and modification)

Time:	6.30 pm on Friday, 26 Aug’05

Venue:	Chua Restaurant, 9 Purvis Street

Attendees:	A/Prof. Luo Fang Lin 	Chair of the 1st ICIEA 2006

A/Prof. Wen Chang Yun	Technical Chair

Dr. Li Zhengguo	Technical co-Chair

A/Prof. Sumedha Rajakaruna	Treasurer

A/Prof. Loh Poh Chiang, Andrew	Local/Social Activity

A/Prof. Singh, Ranjit                          Publication

Dr. Zhu Xing	Publicity

Dr. Xie Wen Xiang	Secretary

Ms. Merlin, Toh Bee Keng	Secretariat – CMC, NTU

Absent with apology:

Mr. Seow Kang Seng	Sponsorship

- Dr. Luo reviewed the work done and current progress of the 1st ICIEA 2006.

- Call for Paper Enhancement: As of today, only one month is left for the deadline for full paper submission. However, we received only 17 papers. Thus, the current urgent task for the committee is how to motivate people to submit papers to the conference. In the coming September, we will be doing: (1) publish the reminder of the deadline in the early September; (2) extend the deadline at the end of September.

- Application the ICIEA 2006 proceedings to be indexed by EI Compendex: In order to absorb more people, especially from China, to submit papers to the conference, it is necessary to make the proceedings of ICIEA 2006 be indexed by EI Compendex.

- Exhibition Status Update by Andrew and Merlin: So far, no confirmation from any company.

- Keynotes/Plenary Talks Update: All confirmed and so far there is no problem raised.

- Invited Session Update: Dr Li suggested that everybody is responsible for each invitation.

- Publication Update: All agreed that the proceedings would be provided in the format of CD-ROM, hard-copy of abstract of each paper instead of hard-copy of full papers.

- Financial Situation and Expenses Update by Merlin: So far, the amount of S$5922.35 was expensed including the hotel deposit.

- Student Registration Rate: This issue was discussed but no agreement.

Let’s take our own part and do it right now to make our conference successful. Thanks.

Prepared by Dr. WenXiang Xie on 29 August 2005