Event Management Proposal

2011 Pulsed Power Conference

17 June – 23 June 2011

Chicago, IL

Date:  3 September 2009

Prepared By:

Elsie Cabrera, CMP

Manager, Conference Planning & Sales

IEEE Meeting & Conference Management

445 Hoes Lane

Piscataway, NJ  08854

P:  + 1 732 981 3428

E:  e.cabrera@ieee.org

www.ieee.org/go/mcm

INTRODUCTION

Thank you for allowing us the opportunity to continue to partner with the IEEE Pulsed Power Conference. We are excited at the opportunity and look forward to further discussions.

Recognized as the premier provider of meeting and conference management for the IEEE, we know the importance of providing the best service possible for the benefit of our clients, while maintaining the lowest possible costs to your bottom line.  We are part of the IEEE Community and will have your best interest in mind.

You can be confident that our team of certified professionals is fully qualified to provide consistent positive results: they are multi-task experts.  We listen carefully, communicate effectively, remain flexible to changes, and stay within your budget. We’ll provide a dedicated team to support you from the start, to assure your event is smoothly executed.

A FULL SERVICE SOLUTION

We can manage your entire event from start to finish or provide assistance in specific areas of your choice. Our complete spectrum of services include contract negotiation, food & beverage planning, venue & supplier management, registration, on-site support, staging and equipment, entertainment, and all of the special touches that will make for a successful event.

Our team of certified meeting professionals will create an event to meet your objectives and exceed your expectations.

Available Services:

- Budget and objective guidance

- Site selection, negotiation, and contract review

- Meeting Announcements, Reminders, and Past-Due Notices

- Menu Planning

- Audio-Visual Planning

- On-Site Management

- Transportation/Airline Reservations

- Account Reconciliation and Reporting

- On Line Registration

- On Line Hotel Block Management

BENEFITS OF OUR GROUP

IEEE MCM knows every angle of the event planning business. Our team has the knowledge, resources and experience to guide you through all the details. We manage over 200 events every year for both domestic and international clients, ranging from 20 to 15,000 attendees.

Choosing IEEE means you will form a partnership with a focus on quality to deliver a highly tailored and customized model for your event management needs. Your IEEE MCM team will take care of the logistical details, allowing you to focus on the big picture.

What benefits can we offer?

- Full Service Management Company

- Experience managing events around the globe

- CMPs – Our planners have earned the designation of Certified Meeting Professional

- Multi-task experts, accustomed to handling multiple concurrent deadlines

- Dedicated to providing superior service

- Excellent communicators, intuitive and able to anticipate the smallest of details

IEEE MCM EXPERIENCE

IEEE MCM has managed over 200 different technical meetings, conferences and symposia over the last ten (10) years. We have handled a variety of services for these events, from providing pre-registration services to handling every aspect of the conference/symposia for the committee.

IEEE-MCM has experience managing conferences from 20 to 15,000 attendees.

Lead Conference Planners

With every conference IEEE MCM manages, a lead conference planner is assigned to serve as the main point of contact for the conference committee, the IEEE MCM staff and all contracted vendors.  The lead conference planner will work closely with the committee on all activities of the conference.  We have experienced that assigning overall responsibility to our lead conference planner creates a sense of ownership and pride, producing end results that are truly amazing.

Our conference planners are considered subject matter experts and will:

- Serve in an advisory role on how to run an IEEE conference (often asked for comparison against what other IEEE conferences do) (opportunities/best practices)

- Conference delivery from the “non technical” perspective

- Provide strong historical perspective on the conference for appropriate recommendations

- Have strong knowledge of the varied IEEE sponsorship opportunities and liabilities associated with each

- Aid in budget preparation

- Have thorough understanding of the technical program development from original paper submission and peer review process, acceptance, program build, and content delivery pre/post conference

- Provide guidance/support on compliance activities (ways to reduce to obstacles)

The lead planner will direct the IEEE MCM team assigned to the event and keep the client informed of the progress of all aspects of the conference.  Our permanent in-house conference support staff is accustomed to providing professional, friendly service in an efficient manner.  They are experts at multi-tasking and extremely effective in meeting all the demands of multiple concurrent deadlines, consistently.

STATEMENT OF WORK

| logistics Pre plannig/coordination & onsite |
| --- |
| pRICING: Pre-planning & coordination onsite management Site visits/committee meetings | $30,000 Flat Fee $900 per day plus Travel &Living Expenses per person $95 per hour (Travel &Living Expenses costs are covered by conference) |

IEEE MCM will work with volunteer leaders and designees to plan all aspects of the event.  We will serve as the direct liaison with all vendors and venues, sales and management staff to communicate the needs of the group.  Key details include:

- Initial consultation and introduction with committee to develop an agreed upon joint timeline incorporating key milestones based on conference needs

- Coordinate/attend steering committee meetings (as needed, either in person or via conference call)

- Consistent and timely communication with the committee and designees throughout the planning stages of the conference

- Manage and plan hotel/convention center space for all events

- Negotiate vendor contracts

- Negotiate any required amendments to the contract to be approved and signed by the committee and IEEE Procurement on a timely basis

- Arrange meeting rooms setups. Detail each room utilized by the conference with regards to set-up, A/V, sound and food & beverage

    - Arrange for and manage all food functions.  Select menu in coordination with chair or designee

    - Arrange for and manage audio visual requirements

- Maintain close liaison with hotels as necessary to communicate changes in group requirements (e.g. guest room block, meeting space, food & beverage, network, social, upgrades, etc.)

- Serve as direct liaison for the committee, vendors and venues, minimizing the possibility of details being overlooked

- Work with general chair or designee on providing instructions for VIPs, complimentary room assignments, special event coordination, VIP seating, etc.

- Provide billing instructions and all other pre-conference pertinent information, as required by committee and coordinated with finance chair for payment

- Assist technical program chairs in determining meeting room requirements, speaker’s prep room, and assigning rooms for technical sessions

- Order all necessary signage – contract vendor, design, oversee production and printing of signage including but not limited to breakout meetings, technical sessions, directions, social events, registration and banners

- Arrange for security personnel if necessary

- Arrange for onsite communication provisions, if necessary

- Arrange for shipping and storage

- Conduct pre-conference meeting with the chair and key conference volunteers

- Conduct pre-conference meetings with the hotel/convention center to confirm and review of conference in detail

- Ensure steering committee room (if applicable) arrangements including phones, two-way radios, computers (with DSL or equivalent), copiers, printers (networked to computers), during hours of operation

- Coordinate and manage a guest hospitality suite (if applicable). The steering committee will arrange for staffing of guest hospitality suite during hours of operation. Refreshments will be served as specified by the committee.  Arrange additional services: computer with internet access for e-mail, phone and CVB hospitality desk

- Coordinate with the photographer and manage all requested photographs as directed by committee (if applicable)

- Work with the steering committee to develop a transportation plan (if applicable)

- Monitor expenses levels – report deviations or possible budget variances

- Provide status reports to the conference chair or designee leading up to the event

- IEEE MCM will provide an updated detailed report of the group's history, pick-up, and meeting room requirements and spend at the end of the event

on site Logistical management

IEEE MCM will work with volunteers to ensure that all operational tasks are completed during the event. Committee will provide a workforce of able volunteers for various activities.

IEEE MCM will meet with vendor and venue staffs, prior to the conference to confirm and review all final decisions and logistics.  During the conference IEEE MCM will serve as the direct liaison with all vendor and venue, management and operations staffs to ensure the needs of the conference are met including:

- Monitor and provide guidance for volunteer run functions

- Monitor conference social and hospitality functions

- Monitor food & beverage functions.  Keep an eye on levels of consumption, order more if necessary with concurrence of the chair or designee, and advise of possible budget variances. Food and beverage cost is to be minimized, but should not diminish attendee experience

- Set up and maintain committee operations room, if necessary

- Secure and Maintain storage space for signage, audio visual, and other conference materials not secured in Registration area

- Ensure adequate food and beverage in guest hospitality suite. Committee will arrange for staffing of guest hospitality suite during hours of operation

- Handle crisis and emergency management in conjunction with facility staff.

- Ensure all contract obligations are met by all parties

- Serve as direct liaison between committee and hotel/convention center staff/vendors

- Track shipping for all known deliveries

- Ensure correct signage placement

- Field requests and complaints of key volunteers

- Review final hotel room pick up report daily

- Review food & beverage invoices daily

- Monitor session area and other contracted space to ensure room arrangements, food & beverage and audio visual are being provided according to contract

- Meet with the hotel/convention center daily to review prior day’s charges and next day’s changes, including banquet event orders. Review and approve or deny as needed

- Reconcile and approve all invoices to ensure accuracy prior to submitting for payment

- Inspect meeting room layouts for set-up and audio visual before each session or meeting

- Monitor audio visual contractual performance

- Rent appropriate equipment for speaker prep room in coordination with the audio visual contractor

On site staffing requirements are based on:  scheduled concurrent events occurring in multiple locations, the various needs for those events and the availability/willingness of either committee members or volunteers to oversee those events.  While we recommend a trained staff member be assigned to each location where a major event or multiple small events are taking place, we have had (at the request of past Executive Committees to minimize expenses) committee members or volunteers fill in.  The committee will have the final decision in that regard, IEEE MCM will assist you in making an appropriate decision.

Post Conference

Upon conclusion of the conference, IEEE MCM will work with volunteers to document key features of the conference including successes and lessons learned.  Specifically:

- Compose a summary report of meeting for file and committee review

- Conduct post-conference meetings with executive committee and conference volunteers

- Conduct post-conference meetings with hotel/convention center

- Prepare a final financial report summarizing all budgets, actual costs, outstanding expenses, and budget variances

| registration management |
| --- |
| pRICING: Website Development registration Cancellations/Badge only Onsite registration management Additional registration staff support Purchase orders/wire transfers | $900 Flat Fee (allowance for up to three rounds of edits) $16.50 per Attendee $7 per cancellation/badge only $650 per day plus Travel &Living Expenses $550 per day plus Travel & Living Expenses (if applicable) $15 per |

Our offering includes a suite of services designed to facilitate an attendee’s entire event experience. Starting with the event communication through a customized online registration website and print form for advance registrations, to onsite registration management provided by knowledgeable registration personnel to welcome your attendees.

Full registration management inclusions:

- Dedicated management professional

- Advance registration

- Registration packet creation

- Onsite registration management

- Financial processing

Dedicated Management Professional

We will provide you with a dedicated registration management professional who be your expert guide in development of the online registration form specific to your conference needs. We will manage any issues during pre-launch and help guide you along the way to ensure you have captured the right data for your conference tracking needs.

Advance Registration

- Secure PCI Compliant on-line registration system available worldwide, 24 hours a day, 7 days a week

- Design and maintain customized conference registration website

- Provide registration URL to add as hyperlink to your conference website

- Create hard copy registration form

- Dedicated email address for registration questions and assistance

- Toll free number (US & Canada) and a direct dial for international attendees

- Receive and process registrations received by mail or fax

- Manage all payments via credit card, check, wire transfers and purchase orders

- Process cancellations and refunds

- Balance due collection

- Real Time - Report Generation (A complete list/description of reports can be found within the appendix)

- Automated e-mail confirmations within 24 hours

- Review and maintain database to be free of entry errors or omissions as well as clean up of any duplicate registrations

- Website troubleshooting and support to client

Registration Packets Creation

Inclusive of our advance registration package pricing, we will supply you with customized materials for your event registration packet which will include:

- Badge design creation for your review prior to print

- Badge printing

- Banquet and drink tickets as needed

- Attendee ribbons from our standard stock of over 20 different categories

- Name badge holders

- IEEE MCM lanyards

- Confirmation/receipts for attendee

- Welcome packet envelopes

- Flag any balance dues

- Tag any VIPs for a more personalized experience if desired

- Proof all registration packets against registration lists as a check and balance

We are happy to customize registration packet materials based on your needs and only ask that you cover the differential in cost for these highly personalized requests.  Shipping materials to your conference location will be provided at a pass through cost to the conference.

Onsite Registration Management

We will design, setup, and manage the onsite registration experience, ensuring your attendee’s experience is a positive one from the moment they enter the facility.  We will:

- Establish a pre-registration area (booth/desks) for attendees arranged alphabetically which will provide for ease and flow of the registration experience

- Provide personnel as needed to ensure appropriate support

- Order equipment needed (i.e. internet lines, printers, self-service computers if needed)

- Set-up/dismantle registration area

- Process onsite registrations, refunds, and additional purchase items

- Provide real-time registration reports at the conclusion of each day and advise of any increases to specific functions for guarantee adjustments

| exhibit management |
| --- |
| pRICING: Exhibit management onsite management | 15% of total booth sales $850 per day plus Travel & Living (Exhibit Manager) |

IEEE MCM will work with the conference committee on exhibit advance planning, exhibit space sales exhibit management and exhibit finances.  We will serve as the direct liaison with all vendors and exhibitors:

- Develop a time line and budget

- Work with decorator/venue/vendors

- Prepare sales prospectus and service kit

- Sell exhibit space (client must provide list to contact)

- Maintain records

- Manage booth assignment

- Collect contracts and payments, invoice as necessary

- Establish and maintain exhibitor prospect list

- Send out RFP for air freight carriers, lead retrieval contractors; computer equipment rental, floral, photographer, etc. (working with conference planner)

- Develop final exhibitor program

- Provide weekly status reports

- Conduct pre-conference meetings with convention center

- Order and place all necessary signage in exhibit hall

- Arrange for security personnel

On-Site Exhibit Management

- Supervise floor marking with decorator and general move in

- Collect any unpaid balances from exhibitor

- Check floor for booth violations

- Check on special areas and hanging of banners and signs

- Oversee entrance units and meter board placement

- Circulate through show to answer questions and resolve any issues

- Second and third day – hands out contracts and floor plans for the following years

- Oversees move – out and general cleaning

- Review decorator’s bill on site with account executive

Post Event Exhibit Management

- Review bills and send to exhibit chair for final approval

- Send out post show survey to all exhibitors

- Recap results of survey and send to exhibit chair for review

| financial management |
| --- |
| pRICING: | $1,500 Flat Fee |

IEEE MCM will provide the following bonded financial management services to the conference:

- Provide guidance to Conference Treasurer on IEEE Policy & Procedures

- Review all invoices to ensure accuracy prior to payment

- Submit payment for committee approved invoices

- Maintain detailed financial records (MCM activity only; income deposited, expense paid, and transfers made by MCM, using our internal general ledger accounts)

- Provide monthly cumulative report (summary and transactions) to conference treasurer (MCM activity only; income deposited, expense paid, and transfers made by MCM, using our internal general ledger accounts)

- Record retention for reconciliation and/or audit purposed

Below portion available only will full management events.  If you choose not to use IEEE MCM for registration, the conference treasurer would be responsible for the below.

- Submission of year end accruals to IEEE Conference Services (to meet IEEE obligations for conference not closed by the end of the year)

- Prepare the final financial report

    - Includes activity for all accounts

    - Treasurer/conference chair must approve final report before submission to Conference Services

- Administer closing aspects of conference

    - Distribution of surplus

    - Submission of final reports to IEEE Conference Services, IEEE Audit, conference committee

    - Completion of IEEE Conference Services financial form

    - Guide committee on their responsibilities in conference closing

    - Completion of financial forms/documents required by IEEE Conference Services

- Coordinate audit (required for IEEE financially sponsored events with $100k revenue or expenses)

    - Gather financial records (income & expense)

    - Submit financial records to IEEE Audit

    - Respond to IEEE Audit inquiries

    - Monitor progress with IEEE Audit to confirm audit completion

FINANCIAL PROCESSING

All financial transactions are secure as we must adhere to the International Payment Card Industry Standards (PCI) for payment collection.  Our current payment gateway is Authorize.net and our SSL is VeriSign.  These are the approved payment collection methods for all IEEE credit card transactions.

Form of payment that can be used with on-line registration is limited to credit card transactions.  Card types currently accepted along with 2010 rates are:

- Visa, Master Card, Discover – 2.9%

- American Express – 4.0%

*Rates are subject to change based on market fluctuation.

Funds are maintained within the IEEE system and the following process is utilized:

- Payments processed real-time

- All income deposited into your designated conference banking account

- Checks or wire payments will be made in US dollars (wire payments will incur a $20 charge per wire transfer)

- IEEE holds a small amount varying on the size of the event to cover any charge backs that might occur

Pricing Structure

| Service | Comments | Unit Price (USD) | Unit |
| --- | --- | --- | --- |
| Logistics | Pre-Planning & Coordination | $30,000 | Flat Fee |
|  | Onsite Manager | $900 | Per day plus T&L |
|  | Site Visits/Committee Meetings | $95 per hour | Plus T&L |
| Registration | Website Development | $900 | Flat Fee |
|  | Website Changes post approval | $90 | Per hour1 |
|  | Registration | $16.50 | Per registrant2 |
|  | Cancellations | $7.00 | Per cancellation3 |
|  | Badge Only | $7.00 | Per badge only4 |
|  | Purchase Orders/Wire Transfers | $15.00 | Per PO/WT5 |
|  | Onsite Registration Manager | $650 | Per day plus T&L |
|  | Additional Onsite Registration Staff | $550 | Per day plus T&L |
|  | Discounted Credit Card Fees*** | 3% | Average6 |
| Exhibit Management | 15% of booth sales | $11,475 | Est on 2009 actuals |
|  | Onsite Exhibit Manager | $800 | Per day plus T&L |
| Financial Management | Flat Fee | $1,500 | Flat Fee |

1 This fee will only be charged if the committee makes changes to the website after it is originally approved and activated.

2 Registrant is defined as any individual entered into the MCM registration system and a confirmation number is assigned.  You will only be charged for the actual number of registrants.

3 If multiple registrations are created by an attendee, the conference will be charged $16.50 for the initial reservation and $7.00 to cancel each duplicate. If an attendee needs to cancel, the $7.00 fee will also apply.

4 Committees can register a select group of non-paying individuals without being charged the full registration fee.  Not to exceed 5% of total registrations.

5 When an attendee chooses to pay for their registration by either Purchase Order or Wire Transfer, the conference will be charged a $15.00 additional processing fee for that registrant.  You may elect not to offer payment by Purchase Orders or Wire Transfers.

Current Visa, MasterCard, Discover rates are 2.5%; AMX rates are 4% (average 3%).  Credit card rates are subject change w/o notice due to bank adjustments

Pricing Extras

IEEE MCM fees and complimentary extras relate only to the agreed upon services detailed above.  All other direct expenses (i.e. credit card and wire transfer fees, printing, advertising, supplies, postage, shipping, transportation, equipment rental, decorator, security, on-site telephone charges and third party charges for equipment or services not provided by IEEE.) are to be paid by the conference.

Client shall also be responsible for Staff Salary ($95.00 per hour), plus Travel and Living Expenses for any meeting(s) that would require the Conference Planner or a designate to be present.

MCM staff will travel at the lowest available coach fare. Food and beverage expenses will not exceed $75.00* per person, per day.  (*Subject to change in accordance with IEEE per diem)

Such disbursements shall be direct expenses allowed for in the conference budget and approved by committee.  IEEE MCM will supply the client with a break down of all disbursements incurred.