## Sheet1
ICOPS/SOFE
June 26-30, 2011
Chicago, IL USA
Timing | Date | Completed | Action/Description (IEEE-required actions are bolded.) | Responsibility | Subcommittee | Comments
18-24 months prior to conf |  |  | Agreement (MOU) between conference sponsors Note: All Contracts & MOUs with a value of $25,000 or more must be reviewed and executed by IEEE Procurement.
18-24 months prior to conf |  |  | Appoint General Chair; establish Local Organizing Committee (LOC); notify sponsoring organization(s) of General Chair
18-24 months prior to conf |  |  | Initial meeting of conference committee to select conference name, theme, location, date, venue Note: Check for potential conflicts with other IEEE conferences | LOC
18-24 months prior to conf |  |  | Contract with IEEE Conference Management for conference venue contract site selection & contract negotiation, registration management, conference logistics, etc. | LOC
18-24 months prior to conf |  |  | Contract with conference venue and overflow hotels if needed (send out RFP, review proposals, negotiate contract) Note: All Contracts with a value of $25,000 or more must be reviewed and executed by IEEE Procurement. | MCM
18-24 months prior to conf |  |  | Submit IEEE Conference Information Schedule to IEEE Conference Services for listing in the Conference Search Database and Call for Papers | LOC
18-24 months prior to conf |  |  | Submit Conflict of Interest forms to IEEE Conference Services | LOC General Chair & Treasurer
18-24 months prior to conf |  |  | Submit IEEE Conference Budget Forms (Summary, Income, Expense & Social Functions) to IEEE Organizational Unit for approval | LOC Treasurer / MCM
18-24 months prior to conf |  |  | Contact IEEE Conference Services to open up a concentration banking account | LOC Treasurer / MCM
18-24 months prior to conf |  |  | Request loan (seed money) from Sponsoring Society to be deposited in the concentration banking account | LOC Treasurer / MCM
15-18 months prior to conf |  |  | Create theme and logos. | LOC | Marketing
15-18 months prior to conf |  |  | Obtain domain name and create web site | LOC | Webmaster
15-18 months prior to conf |  |  | Develop Advertising program/publicity (brochures, post cards, ad pages, posters, etc) | LOC | Marketing
15-18 months prior to conf |  |  | Develop promotion plan for booth at current year's conference (table top display, give-a-ways, etc.) | LOC | Marketing
15-18 months prior to conf |  |  | Research magazines & trade publications to advertise in. Note publication deadlines. | LOC | Marketing
12-15 months prior to conf |  |  | Hire Decorator for exhibits (send out RFP, review proposals, negotiate contract, create floor plan) | MCM
12-15 months prior to conf |  |  | Create Exhibitor Prospectus (application, floor plan, additional selling information) for distribution | MCM
12-15 months prior to conf |  |  | Create Sponsorship and Advertising Opportunities for distribution at current year's conference | MCM
12-15 months prior to conf |  |  | Review and reconfirm hotel and meeting facilities | MCM
12-15 months prior to conf |  |  | Meeting of Conference Committee, preferably at conference site | MCM / LOC
12-15 months prior to conf |  |  | Preliminary planning of off-site events, tours, etc. | MCM / LOC
12-15 months prior to conf |  |  | Determine format for proceedings, i.e. print, CD, both | LOC | Publications
12-15 months prior to conf |  |  | Submit IEEE Conference Publications form | LOC | Publications
12-15 months prior to conf |  |  | Determine topic areas, format, and types of technical papers | LOC | Technical Program
12-15 months prior to conf |  |  | Establish open and close dates for abstract submission, author notification, and final paper submission | LOC | Technical Program
12-15 months prior to conf |  |  | Finalize Call for Papers for distribution at current year's conference | LOC | Publications
12-15 months prior to conf |  |  | Identify presenters for special sessions and invited papers | LOC | Technical Program
12 months prior to conference |  |  | Review contracted hotel room block against current year's pickup and increase/decrease if needed | MCM
12 months prior to conference |  |  | Review budget and update if necessary | MCM
9-12 months prior to conf |  |  | Request permission from related IEEE societies to market to their members | LOC | Publications
9-12 months prior to conf |  |  | Distribute electronic and/or hard copy of Call for Papers to members of sponsoring and related IEEE societies as well as non-member attendees of previous conferences. Post on conference web site. | LOC / MCM | Publications
9-12 months prior to conf |  |  | Send Call for Papers to IEEE Conference Services to post on IEEE conference web site. | LOC / MCM | Publications
9-12 months prior to conf |  |  | Establish a unique web site for authors that hosts the conference publication schedule, instructions for submission of author abstracts/final papers as well as IEEE copyright agreement, FAQs, and support contact information. | IEEE Conference Publications
9-12 months prior to conf |  |  | Design electronic author kit with conference-specific instructions and incorporate into peer review site. | IEEE Conference Publications
9-12 months prior to conf |  |  | Post CFP to Website | LOC | Webmaster
6-9 months prior to conference |  |  | Send committee meeting request forms to technical committees to schedule meetings during conference | MCM
6-9 months prior to conference |  |  | Complete conference registration questionnaire and submit to MCM. | TDMG | Registration
6-9 months prior to conference |  |  | Create online registration forms and send URL to LOC for review | TDMG
6-9 months prior to conference |  |  | Create hard copy registration form based on final online form | TDMG
6-9 months prior to conference |  |  | Obtain merchant account for credit card processing | MCM
6-9 months prior to conference |  |  | Post online registration link and hard copy file on conference web site | TDMG | Webmaster
6-9 months prior to conference |  |  | Send registration report access to LOC | TDMG
6-9 months prior to conference |  |  | Review paper abstract submissions | LOC | Technical Program
4-6 months prior to conference |  |  | Early Exhibitor Discount Registration cut-off date Send eNotice reminder of deadline 1 week before | MCM
4-6 months prior to conference |  |  | Preliminary assignment of exhibit space to early exhibitors Exhibit space assignment ongoing as new exhibitors register | MCM
4-6 months prior to conference |  |  | Paper review completed and program finalized. Papers arranged into sessions. | LOC | Technical Program
4-6 months prior to conference |  |  | Provide program details to Publication Chair for printing in Advance Program. | LOC | Technical Program
4-6 months prior to conference |  |  | Notify Speakers and Session Chairs of acceptance or rejection. | LOC | Technical Program
4-6 months prior to conference |  |  | Advance Program designed, printed, and mailed. | LOC/MCM | Publications
4-6 months prior to conference |  |  | Distribute electronic and/or hard copy of Advance Program to members of sponsoring and related IEEE societies as well as non-member attendees of previous conferences. | MCM
3-4 months prior to conference |  |  | Final papers and copyright release forms submitted. Late authors contacted. | LOC | Technical Program
3-4 months prior to conference |  |  | Author manuscripts (source files) converted to IEEE Xplore-compliant PDFs. | IEEE Conference Publications
3-4 months prior to conference |  |  | Organize papers as indicated by the conference-provided list of papers for proceedings publication. (This list of papers becomes Table of Contents.) Add page numbers. Create author index. Create copyright page. Design Book/CD cover. | IEEE Conference Publications
3-4 months prior to conference |  |  | Bids solicited from printers and/or CD/ USB manufacturers | IEEE Conference Publications
3-4 months prior to conference |  |  | Publication files sent to book printer and/or CD/USB manufacturer | IEEE Conference Publications
3-4 months prior to conference |  |  | Book Print/CD/USB Prototype reviewed | IEEE Conference Publications & LOC | Technical Program & Publications
3-4 months prior to conference |  |  | Request weekly reports from hotel on room pickups up to week of Symposium. Increase/decrease block if needed. | MCM
2-3 months prior to conference |  |  | Develop volunteer job functions/needs list Solicit student volunteer assistance from local universities | LOC | Volunteers
2-3 months prior to conference |  |  | Order attendee giveaways (bags, pens, etc.) | MCM
2-3 months prior to conference |  |  | Order speaker gifts | MCM
2-3 months prior to conference |  |  | Order conference organizing committee shirts and student volunteer shirts | MCM
2 months prior to conference |  |  | Final publicity in IEEE publications | LOC | Publications
1-2 months prior to conference |  |  | Conference Planning Staff make travel arrangements | MCM
1-2 months prior to conference |  |  | Early Registration cut-off date Send eNotice reminder of deadline 1 week before | MCM
1-2 months prior to conference |  |  | Send preliminary specs (set up, catering, etc.) to conference venue | MCM
1-2 months prior to conference |  |  | Create AV RFP and send out to in-house and IEEE preferred vendors for quote | MCM
1-2 months prior to conference |  |  | Order signage | MCM
1-2 months prior to conference |  |  | Orders plaques and certificates for awards and acknowledgements | LOC / MCM | Awards
6 weeks prior to conference |  |  | Final Program designed, printed, and shipped to conference site. | MCM / LOC | Publications
6 weeks prior to conference |  |  | Order equipment for on-site registration: tables/reg counters, printer(s), high-speed internet access, power supply, phone line, wastebaskets | TDMG
6 weeks prior to conference |  |  | Determine Multipurpose Criteria (badge stock design) | TDMG | Registration
6 weeks prior to conference |  |  | Order Multipurpose Paper (badge paper) | TDMG
6 weeks prior to conference |  |  | Determine Badge Ribbon Criteria | TDMG | Registration
6 weeks prior to conference |  |  | Order Badge Ribbons | TDMG
6 weeks prior to conference |  |  | Determine Badge Holder Criteria | TDMG | Registration
6 weeks prior to conference |  |  | Order Badge Holders | TDMG
1 month prior to conference |  |  | Finalize Volunteer Roster | LOC | Volunteers
1 month prior to conference |  |  | Hotel room block deadline. Review pickup. Request extension if needed. Send eNotice reminder of deadline 1 week before. | MCM
1 month prior to conference |  |  | Books/CDs/USBs shipped to conference site and delivered to IEEE Conference Publications per Letter of Acquisition. | IEEE Conference Publications & MCM
1 month prior to conference |  |  | Send early registration list to registered exhibitors | MCM
14 days prior to conference |  |  | rt | TDMG
14 days prior to conference |  |  | Check requests for final deposits and speaker honoraria | MCM
7-10 days prior to conference |  |  | Create On-Site Registration Form | TDMG
7-10 days prior to conference |  |  | Prepare registration materials; print confirmations and badges | TDMG
4-5 days prior to conference |  |  | Pack and Ship registration materials | TDMG
1-2 days prior to conference |  |  | On site pre-conference meeting with conference venue staff | MCM
1-2 days prior to conference |  |  | Registration set up and on site registration opens | TDMG
1-2 days prior to conference |  |  | Exhibitor set up at conference venue | MCM
14 days post conference |  |  | Preliminary conference report on attendance, solvency, and inventory of conference proceedings | LOC / MCM
21 days post conference |  |  | Registration Manager processes refunds, invoices for balances due, etc. | TDMG
30 days post conference |  |  | Send thank you letters to sponsors with attendee list and information about sponsoring the following year's conference | MCM
30 days post conference |  |  | Send thank you letters to exhibitors with attendee list and information about exhibiting at the following year's conference | MCM
30 days post conference |  |  | Make arrangements for a Professional Independent Audit | Treasurer
30 days post conference |  |  | Repay all Conference Loans | Treasurer
45 days post conference |  |  | Registration Manager invoices conference | TDMG
45 days post conference |  |  | Registration Manager send Wrap-Up Reports to LOC (category report, activity report, etc.) | TDMG
3 months post conference |  |  | Submit Preliminary Financial report to IEEE Organizational Unit | Treasurer
6-12 months post conference |  |  | Distribute of remaining surplus and close bank account | Treasurer
6-12 months post conference |  |  | Submit Final Financial Report and Audit to IEEE Conference Services | Treasurer
By January 10th of year following conference |  |  | Complete W-9 information and send to IEEE Accounts Payable | Treasurer