## Overview
IEEE PSES BOD Activities Dashboard
Overview
2017-03-07
Purpose - | The purpose of the 'Dashboard' is to provide an overview of the current status of PSES activities to allow for easy tracking and managment. In particular, 'Tactical Activities' flow directly from our Strategic Plan and represent those plan items that have been selected as a high priority to develop. As such this document serves as our 'live 'Operational Plan'.
The intent is to update this 'Dashboard' on a monthly basis prior to our BOD meetings so we have an efficient view into our current activities.
Each type of activity will have a short description of the activity, expected completion time, who is responsible and current status (green/on track, yellow/in danger, red/problems).
Although not all activities will flow directly from the Strategic Plan (i.e. - Action Items), they should all support the Strategic Plan in some way. We will expect all activities to be completed as scheduled so we can move on to other activities. If circumstances necessitate a change in timing, activity scope, etc. the BOD will discuss/approve and change accordingly. I have also added a "Parking Lot" for possible future actions to consider.
Note - as can bee seen all actions, activities, etc. have a lead identified. Any proposal for some action or activity by the Board or Society should include a recommendation as well as a lead who will follow through with the recommendation.
Structure - | The Dashboard is divided into the following by separate Workbook Tabs:
Action Items - These will typically be short term activities established at BOD meetings - they would typically not be expected to remain on the list for longer than 3 months.
Tactical Items - These will be longer term activities that flow from or are connected to specific Strategic Plan Objectives. Note, these will include only those prioritized tactical measures from the plan that are actively being worked on at any one time (suggest no more than three active at any time for each plan item and no more than 5 total and then when one is finished the next priority item will be maybe active)
Conferences - These will be formally scheduled Conferences for which the PSES has committed to participate or co-sponsor in some fashion.
BOD Reference - This is a simple directory of BOD members, committee chairs, committee members and Liaisons. This includes identification of open colunteer positions as well as a list of potential member/volunteer resources!
Parking Lot - this is a simple list of ideas that did not have a commitment for formal action, but were of potential future interest.

## Action Items
Action Items
2017-05-07
Date | Action Item Description | BOD Lead | Planned Completion Date | Status | Comments
2017-02-02 | Grant to be EMC Sister Society Representative | John / Grant | Start June, 2017 |  | Need a counterpart from EMC-John to talk to Frank at TAB in June. Compliance 101 at EMC 2018.
2017-02-02 | Fellows Committee formed | John / Stefan | 2017-11-01 |  | Stig Nelson is Chair for 2017. Need Chair for 2018. Jim Nitten. Need to follow up
2017-02-02 | Systems Council | Tom L |  |  | What's the role/duties and schedule for meetings? Budget needed?
2017-02-02 | EMC Symposium | John / Murlin | August 7-11, 2017 |  | John and Murlin going. Had a short conversation. Need hand out materials.
2017-02-02 | Newsletter content | Mariel / Silvia |  |  | 1. Need consistent stream of content 2. John to engage Verbal Ink.
2017-02-02 | Formal Papers | Don G |  |  | Need plan
2017-02-25 | VP budgets | Dan | 2017-04-30 |  | Budgets and description of what's being done with the money.
2017-02-25 | Newsletter publishing | Mike | 2017-05-07 |  | Need plan to trigger requests for content, getting it out on time, getting it on the website. Fix eblast issues
2017-02-25 | Strategy Meeting for May meeting | John | 2017-05-07 |  | Create structure, write Agenda
2017-02-25 | Present Compliance 101 at I2MTC | John | 2017-05-22 |  | Need sales materials to hand out
2017-02-25 | Sections Congress | John / Stefan | August 11-13, 2017 |  | Need materials for booth, need people to man the booth
2017-02-25 | IoT MOU | John | 2017-05-07 |  | Do we participate?? $5000/year for three years. If so, need Representative. Decided to not participate.
25-Fed-17 | IEEE Entrepreneurship | John |  |  | Develop relationship. Wants us to educate start ups. Need Lead to drive relationship.
2017-02-25 | PSMA | John | 2017-05-07 |  | Need Lead to drive relationship and Representative on PSMA Committee
2017-02-25 | Society SWOT | John | 2017-05-07 |  | Strength, Weaknesses, Opportunities, Threats - How are we governing? What improvements are needed? Which Societies are best fit to target?
2017-03-07 | Propose Compliance 101 & 201 plan | John | 2017-05-07 |  | Get input on idea
2017-03-16 | Standards Committees | John |  |  | Steli is interested
2017-03-16 | Division VI | John |  |  | Need a representative to lead
2017-03-16 | Document storage | John | 2017-05-07 |  | Decide on one place to put all documents
2017-08-01 | CEDA Article |  |  |  | Need a team
2017-08-01 | Industry Resource Partners |  |  |  | Need a leader
2017-08-01 | Tutorial Book | Stefan
2017-08-01 | Marketing Study - How many IEEE members are practioners?
2017-08-01 | Assistant/Staff
2017-08-01 | IECEE Relationship
2017-08-01 | In-Compliance relationship - we should be feeding them articles
2017-08-01 | Article writing - Company will take verbal and convert to article $100.00
2017-08-01 | Videos/VR via IEEE
2017-08-01 | Gifts for departing BoG members??
2017-08-01 | IEEE Resources - what's available to us?
2017-08-01 | IEEE Publications - surplus sharing from June TAB. What's it mean to us?? | John
2017-08-01 | APEC - Submit proposal | John | 2017-09-01
2017-08-01 | CEDA Compliance 101 ppt | John | 2017-08-18
2016-12-06 | Updated Final Constitution and By-Laws provided by Kevin for all to review for vote at next meeting. | Kevin | 2017-01-31 | Done 07FEB17
2016-12-06 | Updated Final Operations Manual provided by Kevin for all to review for vote at next meeting. | Kevin | 2017-01-31 | Done 07FEB17
2016-12-06 | Kevin to update Dashboard for next meeting. | Kevin | 2017-01-31 | Done
2016-12-06 | Order to be placed for 2017 Symposium gifts. | Mariel | 2016-12-31 | Done

## Tactical Activities
Tactical Activities
2017-03-16
Note - these Tactical Activities flow directly from our Strategic Plan Published March 15, 2015 . |  | Need to review updates all Tactical Plans & Achievements, update and re-prioritize by March 2017.
Related Strategic Plan Objective Note: See related detail on Tactics in the Strategic Plan | Strategic Plan Reference | Activity Description | BOD Lead, additional members | Planned Completion Date | Metrics | Budget | Status | Comments (including, but not limited to, special resource needs, potential issues to address, milestones, overall assesment of success, etc.)
Provide Educational and Professional Development Products of Value to Researchers and Practitioners World-Wide
| A.c.1 | Conferences | Stefan |  |  |  | In Process | Conferences Committee established and additional PSES Confereces proposed as well as participation in other Society Conferences
| A.c.2 | Chapters | Mariel |  |  |  | In Process | Development of Virtual Chapter underway, in addition to better outreach to existing Chapters
| A.c.3 | Educational Activities Committee | Lead - Steve Brody Team - Tom L, Mariel, Daniece |  |  |  |  | How to manage conflict? This is what's stopping it from moving forward.
ADK Information Services - has a course at St. Louis University. JA joined newletter. "Case for Product Safety Professional Certification"
2017-03-16 | A.c.1-3 | Compliance 101 & 201 - ppts, video's, articles | John Allen / Steve Brody | 2017-12-31
Hierarchy of Safety Standards - Pete Perkins
Steli's book
Image, Visibility and Branding
| B.c.1 | Conferences | Stefan |  |  |  | In Process | See above
| B.c.2 | Pulbications | Stefan |  |  |  | In Process | Proposal for transactions developed and initial work to gain support underway.
2017-03-16 | B.c.3 | PR | John | continuous | Initial Marketing Materials Completed | ok | Maintenance Mode | 11Mar2015 - The initial activity here has been completed with the Refresh of the Website, updated Newsletter and initial Marketing Brochures all intended to provide more member value and help attract new members. From here on we will continue to refine all of these and consider the need for more and continue/bulid the 'marketing team'
2017-03-16 | B.c.7 | Relationships SWOTs - Other Societies, Associations, Industry | John
Foster Member Engagement, Volunteerism, and Membership Development
| C.b.1 | Chapters | Mariel |  |  |  | In Process | See above
2017-03-16 | 2 | Develop behaviors and CPRs for each role | need lead | 2017-06-30
2017-03-16 | 3 | BoG to promote at ISPCE | All
|  | Promote Formal Papers | Don Geis
Get a draft letter together showing the value of doing a formal paper. This will be eblasted end of June. And periodically throughout the year, including at the CFP for ISPCE 2018. We'll also use this for an article in the newsletter and Joe can be doing social media.
Confirm that we can take old articles and/or presentations and turn them into formal papers. If so, review all past newsletters and ISPCE's for appropriate articles, contact the authors and see if they'll do the work of putting it into a formal paper.
Up and coming. This is actually my favorite!! This will show the world we're ahead of the game. Topics we came up with are as follows:
Lithium Batteries - Daren Slee?
Drones - Russ (from California - drinking buddy), Orange County recent speaker
Wearables - Tom Burke and/or Ted Eckert
Autonomous Driving - Angie from Google
Engaging and Mentoring Young Professionals
D.c.1
2
3
Development of Financial Resources
| E.b.1 | Establish Fin Com | Dan, FinCom, Daniece |  |  |  | In Process | Establishing more formalized Budgeting process as well as forms to process and track requests.
2017-03-16 | 2 | Develop plan for VPs to submit a Request for funding | Dan, FinCom, Daniece | 2017-12-31
3
Create and Develop a Long Term Leadership and Succession Plan
| F.c.1 | Develop Roles and Responsibilities for each position | Daniece, Kevin, Officers | Done |  |  | In Process | Descriptions established, need final editing and posting and then move to maintenance mode.
| F.c.2 | Publicize various volunteer positions open within the PSES | Kevin |  |  |  | Maintenance Mode | May 2015 - Initially posted in Newsletter and Website as well as active recruiting during Symposium. Next look to active succession planning for all positions.
3

## Conf. & Workshops
Conferences and Workshops
Note - Items in yellow highlighting are in-process, and should be updated with current status.
Conference Name | Lead Organization | Conference Description | PSES Role | PSES Lead | Conference Date | Status | Comments
2014 ISPCE | PSES | ISPCE | Annual Conference | Kevin Ravo | May 5 - 7, 2014 | completed | San Jose - very successful
2014 IEEE International Symposium on Ethics in Engineering, Science, and Technology, Ethics 2015 |  | 2014 IEEE International Symposium on Ethics in Engineering, Science, and Technology, Ethics’2014 | Technical Co-Sponsor | Elya Joffe | 2015-10-01 | completed | Vancouver, Canada
2014 ArgenCon |  | EMC/Safety Conference | Technkical Co-Sponsor | Elya Joffe | June | completed | Buenos Aries
2014 EMC Symposium | EMC Society | EMC Annual Symposium | PSES Booth | Tom Ha | August 4th - 8th | completed | Raleigh, NC
2015 EMC Conference | EMC Society | EMC Conference in San Jose | PSES Booth | Tom HA | March, 2015 | completed | San Jose, CA
2015 ISPCE - Chicago | PSES | ISPCE | Annual Conference | John Allen | May 18 - 20, 2015 | completed | Chicago - succesful, but under budget
2015 EMC Conference in Dresden, Germany | EMC |  | Regional Conference | Jan Swart | Aug 16 - 22 | completed | Germany - successful - should try again - there was interest
2015 ICCE Berlin | CE | Regional Conference | PSES Track? | Stefan Mozar | Sep 6 - 9 | completed
2015 Safe Mobile Power Workshop and Student Design Contest | CE | Local Workshop hosted by SEIMIC/PSES | No | Mark Maynard | Sep 16 - 17 | completed
2015 Taiwan Workshop | PSES | A one day workshop at the Taiwan National Normal University | Engagement with Taiwan Chapter | Wen-Chung Kao | TBA
2016 Consumer Electronics Product Safety Conference | PSES | CEPSC in Las Vegas, collaborate with CEA at CES. | Potential Conference | Dr Nahum Gershon | 2016-01-01
2016 ISPCE - Orange County | PSES | ISPCE | Annual Conference | Bansi Patel | May 16 - 18, 2016 |  | Completed successfully!
2016 International ISPCE - Taiwan | PSES | Need Official Conference Name | International Conference | Stefan Moser | 2016-12-01 |  | Completed successfully!
2017 ISPCE - Santa Clara | PSES | Possible Rename? | Annual Flagship Conf. | Murlin Marks | May ??, 2017 |  | Intended to be Flagship Conference each year. BOD is currently discussing symposium name change from current ISPCE.
2017 Travelling Workshop - near Boston | PSES | Need Name | Travelling Conference | Steve Brody | Early November 2017 |  | Need update on conference name for marketing and promotion.
2018 ISPCE - Santa Clara | PSES | Possible Rename? | Annual Flagship Conf. | ? Need chair
2018 Travelling Workshop | PSES | Need Name | Travelling Conference | ? Need Chair |  |  | Need location and chair status
2019 ISPCE - Santa Clara | PSES | Possible Rename? | Annual Flagship Conf. | ? Need chair
2019 Travelling Workshop | PSES | Need Name | Travelling Conference | ? Need chair |  |  | Need location and chair status by mid-2017

## BOD Reference
BOD Reference Information
BOD Quick Reference
Note - new entry at bottom for listing of others who may be interested - let's keep this up to date so we have a ready list to contact! | Note - cells shaded in this color are where we need new/additional candidates - please verify and/or provide the name of a candidate or recommend a new candidate to the indicated committee chair. | Action - Need input from everyone on updates to new committee members, etc.
2016 Board of Directors
Name | Role | email | preferred phone | term expires
Board of Directors
Officers
John Allen | Acting President | jrallen@productsafetyinc.com | 630-238-0188 | 2019-12-31
John Allen | President Elect | jrallen@productsafetyinc.com | 630-238-0188 | 2017-12-31 | Becomes President on 01-Jan-2018
Mark Maynard | Past President | mmaynard4work@gmail.com | 512-577-5486 | 2017-12-31 | Becomes Immediate Past President -1-Jan-2018
Kevin Ravo | Immediate Past President | kevin.l.ravo@ul.com | 408-464-2601 | 2017-12-31
Daniece Carpenter | Secretary | daniece@ieee.org | 1.512.728.3237 | 2016-12-31 | Note - may choose to serve another term.
Dan Arnold | Treasurer | Daniel.Arnold@ul.com | 360-921-2726 | 2016-12-31 | Note - may choose to serve another term.
Dan Arnold | Fin Com Coordinator
Stefan Mozar | Fin Com
Mike Nicholls | Fin Com
Fin Com
Fin Com
Fin Com
Mike Nicholls | Vice President Communication Services | mnicholls@A-M-C.COM | 805-389-1935 ext 290 | 2018-12-31 | Note - may choose to serve another term.
| Marketing Committee Coordinator | Billb@productsafet.com |  | N/A | Need replacement for Bill
John Allen | Marketing Committee | jrallen@productsafetyinc.com |  | N/A
Mark Maynard | Marketing Committee | mark.maynard@siemic.com |  | N/A
? | Marketing Committee |  |  | N/A
Jim Bacher/Dave Heald | Email List/EMC-PSTC
Jim Bacher/Dave Heald/Dan Roman | PSES IEEE Communities
Mike Nicholls | Webmaster/Internet
Stefan Mozar | Publications Committee Coordinator | ccmlma@yahoo.de |  | N/A
Prof. Wen-Chung Kao | Newsletter Editor | jungkao@ntnu.edu.tw |  | N/A
? | CE Magazine |  |  | N/A
Stefan Mozar | Transactions |  |  | N/A
John McBain | Contributor
Nahum Gershon | LinkedIn Admin | gershon@mitre.org |  | N/A
Richard Georgerian | Official Photographer | richardg@mesanetworks.net
Mariel Acosta | General Faceless Email List Recipient | mariel@us.ibm.com |  | N/A
Mariel Acosta | Vice President Membership Services | mariel@us.ibm.com | (520)799-4136 | 2018-12-31 | Note - may choose to serve another term.
Murlin | Chapters Coordinator | mariel@us.ibm.com |  | N/A
Murlin Marks | Awards Coordinator | murlinm@ieee.org |  | N/A
Bansi Patel | Region 1-6 Coordinator | patelbansi@yahoo.com |  | N/A
OPEN | Region 7 Coordinator |  |  | N/A
Steli Loznen | Region 8 Coordinator | sloznen@ieee.org | 972 54 7245794 | N/A
Silvia Dias Monnier | Region 9 Coordinator | silviadm@inti.gob.ar |  | N/A
Paul Kealey | Region 10 Coordinator |  |  | N/A
Sung-Jea Ko / Stig Nielson | Fellow Committee
Silvia Dias Monnier | Vice President Technical Activities | silviadm@inti.gob.ar, silencasa@yahoo.com | 54-11-472-4-6200 ext: 6349, cell: 54-91-16-126-4794 | 2018-12-31 | Note - may choose to serve another term.
Glen Lesmeister | Technical Outreach | Glenn.Lesmeister@hp.com |  | N/A
Steve Brody | Educational Activities Coordinator (includes Certification/iNARTE) | eb.joffe@ieee.org |  | N/A
Thomas Lanzisero | Educationl Activities Committee | Thomas.P.Lanzisero@ul.com |  | N/A
Bill Bisenius | Educationl Activities Committee | billb@productsafet.com |  | N/A
Thomas Lanzisero | Technical Committees Coordinator | Thomas.P.Lanzisero@ul.com |  | N/A
Rich Nute | Technical Speakers Coordinator | richn@ieee.org |  | N/A
Grant Schmidbauer | EMC Sister Society MOU Rep
Stefan Mozar | Vice President Conferences | ccmlma@yahoo.de |  | 2018-12-31 | Note - may choose to serve another term.
Stefan Mozar | General Conference Committee Coordinator | ccmlma@yahoo.de |  | N/A
Nahum Gershon | Conference Committee Member |  |  | N/A
Wen-Chung Kao | Conference Committee Member |  |  | N/A
Greg Andrews | Conference Committee Member |  |  | N/A
Paul Robinson | Conference Committee Member
2017
Directors-at-Large
Mariel Acosta | Director at Large | mariel@us.ibm.com |  | 2017-12-31
Thomas Lanzisero | Director at Large | Thomas.P.Lanzisero@ul.com |  | 2017-12-31
Steli Loznen | Director at Large | sloznen@ieee.org |  | 2017-12-31
Bansi Patel | Director at Large | patelbansi@yahoo.com |  | 2017-12-31
Grant Schmidbauer | Director at Large | grant.schmidbauer@nemko.com | 858 967 1889 | 2018-12-31
John Allen | Director at Large | jrallen@productsafetyinc.com |  | 2018-12-31
Harry Jones | Director at Large | 'hpjones.safety@gmail.com' |  | 2018-12-31
Ken Kapur | Director at Large | kenkapur@yahoo.com |  | 2018-12-31
Steven Brody | Director at Large | sbrody@ieee.org |  | 2019-12-31
Fabio Furlan | Director at Large | fabio.furlan@csagroup.org |  | 2019-12-31
Don Gies | Director at Large | don.gies@nokia.com |  | 2019-12-31
Jeff Pasternak | Director at Large | jeff.pasternak@intel.com |  | 2019-12-31
Liaisons
Murlin Marks | CE Society | murlinm@ix.netcom.com
Silvia Diaz Monnier | WIE ( Women in Engineering)
Mike Nicholls | Transportation Electrification Initiative
Mark Maynard Murlin Marks | CE Soc Future Directions
Steli Lozen | IECEE
Ken Kapur | Division VI Nominating Committee | kenkapur@yahoo.com
Steli Lozen | IECEE
Elya Joffe | SSIT
Dr Wahab Almuhtadi | Region 7 | almuhtadi@ieee.org
Steli Lozen | Region 8
Thomas Lanzisero | IEEE Systems Council
Other PSES Members that have Express Interest in More Involvement… let's add more names to the list so we have a stand by list of sorts. Any new initiative will need to have a lead identified.
Name | Chapter
Aziz Orumbaev | Santa Clara Valley | aorumbaev@apple.com
Paul Robinson | Australia | paulrob@au1.ibm.com
Richard Stern |  | rsternent@yahoo.com
Nahum Gershon |  | schmooz@mac.com
Wen-Chung Kao |  | jungkao68@gmail.com
Lijuan Hao |  | lijuanhao89@163.com
Scott Smith |  | scott.r.smith2@hp.com
Tom Brenner |  | Tom.Brenner@lenze.com
Darren Slee |  | dslee@exponent.com
Bill Bisenius |  | billb@productsafet.com
Richard Nute |  | richn@ieee.org
Homi Ahmadi |  | hahmadi@extron.com
Jin Jiang |  | jjiang@eng.uwo.ca
Darren Slee |  | dslee@exponent.com
Lei Wang |  | Lei.Wang@panduit.com
Kim Fung Tsang |  | ee330015@cityu.edu.hk

## Parking Lot
2016-04-04
Parking Lot
Potential Action Item Description | Submitting BOD Member